## Cost
| Forecast Cost | Current Buy | Production Contract Approved | Approved IOC | FRP Decision | Source | Unit Cost | Cost Baseline | Schedule Source |  |  | Procurement Unit Cost | Dev Quant | Proc Quant | Dev Cost Est | Proc Cost Est | Milcon Cost Est | Full Rate Production
A400M (UK) | 2238 | 22 | 2003-05-27 | 2009-02-15 |  | 2015 NAO Major Projects Report.pdf | 101.7273 | FY2013
A400M (UK) | 2710 | 22 |  | 2015-09-15 |  | 2015 NAO Major Projects Report.pdf | 123.1818 | FY2015 |  |  | Note changed from 25
JSF (US) | 233000 | 2866 |  | 2010-2012 |  | 2016_GAO_F-35 Joint Strike Fighter | 81.298 | 2001-10-15 |  |  |  | 68.9341 | 14 | 2852 | 34.4 | 196.6 | 2 | 2012
JSF (US) | 395700 | 2457 |  |  |  | 2016_GAO_F-35 Joint Strike Fighter | 161.0501 | 2012-03-15 |  |  |  | 137.413 | 14 | 2443 | 55.2 | 335.7 | 4.8 | 2019
JSF (US) | 379000 | 2457 |  | 2015-2018 |  | 2016_GAO_F-35 Joint Strike Fighter | 154.2532 | 2015-12-15 |  |  |  | 130.6181 | 14 | 2443 | 55.1 | 319.1 | 4.8 | 2019
[5 empty] | FY2008 | 2011_DOTE_Reasons Behind Program Delays |  | 1998-09-15
[5 empty] | FY2019 | 2011_DOTE_Reasons Behind Program Delays |  | 2010-05-15
MEADS Fire Unit | 21839.4 | 48 | 2004-09-15 | 2017-09-15 | 2017-03-15 | 2013_SAR_PatriotMEADS Combined Aggregate Program | 454.9875 | 2004-08-15
MEADS Fire Unit | 3112.4 | 0 |  | N/A |  | 2013_SAR_PatriotMEADS Combined Aggregate Program |  | 2013-12-15
MEADS Missile | 8056 | 1528 |  | 2011-03-15 |  | 2013_SAR_PatriotMEADS Combined Aggregate Program | 5.2723 | 2004-08-15 |  | MS FUE
MEADS Missile | 9259.8 | 1528 |  | 2014-09-15 |  | 2010_SAR_PatriotMEADS CAP | 6.0601 | 2010-12-15 |  | MS FUE
MEADS Missile | 9503.9 | 1528 |  | 2015-09-15 |  | 2013_SAR_PatriotMEADS Combined Aggregate Program | 6.2198 | 2013-12-15 |  | MS FUE
Army LW155/M777 |  |  |  | 2006-08-15 | 2004-11-15 | LW155_M777_Schedule_2003_12_8yearSequence.csv |  | 2003
USMC LW155/M777 |  |  |  | 2005-02-14 | 2004-11-15 | LW155_M777_Schedule_2003_6_8yearSequence |  | 2003
Army LW155/M777 |  |  |  | 2006-08-15 | 2004-11-15 | LW155_M777_Schedule_2004_13_7yearSequence |  | 1905-06-26

## Schedule
| Forecast Cost | Current Buy | Production Contract Approved | Approved IOC | Source | Unit Cost | Cost Baseline | Schedule Source |  |  | Procurement Unit Cost | Dev Quant | Proc Quant | Dev Cost Est | Proc Cost Est | Milcon Cost Est | Full Rate Production
A400M (UK) | 2238 | 22 | 2003-05-27 | 2009-02-01 | 2015 NAO Major Projects Report.pdf | 101.7273 | FY2013
A400M (UK) | 2710 | 22 |  | 2015-09-01 | 2015 NAO Major Projects Report.pdf | 123.1818 | FY2015 |  |  | Note changed from 25
JSF (US) | 233000 | 2866 |  | 2010-2012 | 2016_GAO_F-35 Joint Strike Fighter | 81.298 | 2001-10-01 |  |  |  | 68.9341 | 14 | 2852 | 34.4 | 196.6 | 2 | 2012
JSF (US) | 395700 | 2457 |  |  | 2016_GAO_F-35 Joint Strike Fighter | 161.0501 | 2012-03-01 |  |  |  | 137.413 | 14 | 2443 | 55.2 | 335.7 | 4.8 | 2019
JSF (US) | 379000 | 2457 |  | 2015-2018 | 2016_GAO_F-35 Joint Strike Fighter | 154.2532 | 2015-12-01 |  |  |  | 130.6181 | 14 | 2443 | 55.1 | 319.1 | 4.8 | 2019
|  |  |  | FY2007 | 2011_DOTE_Reasons Behind Program Delays |  | 1998-09-01 |  | IOT&E
MEADS Fire Unit | 21839.4 | 48 | 2004-09-01 | 2017-09-01 | 2013_SAR_PatriotMEADS Combined Aggregate Program | 454.9875 | 2004-08-01 |  | IOT&E
MEADS Fire Unit | 3112.4 | 0 |  | N/A | 2013_SAR_PatriotMEADS Combined Aggregate Program |  | 2013-12-01
MEADS Fire Unit | 3303.5 | 0 |  | N/A
MEADS Missile | 8056 | 1528 |  | 2011-03-01 | 2013_SAR_PatriotMEADS Combined Aggregate Program | 5.2723 | 2004-08-01 |  | MS FUE
MEADS Missile | 9259.8 | 1528 |  | 2014-09-01 |  | 6.0601 |  |  | MS FUE
MEADS Missile | 9503.9 | 1528 |  | 2015-09-01 | 2013_SAR_PatriotMEADS Combined Aggregate Program | 6.2198 | 2013-12-01 |  | MS FUE
Patriot-MEADS_CAP_December_2012_SAR